# Workforce Disability Equality Standard Delivery Plan 2021-2025

| EDI Strategic Plan Objective | Actions | Accountable Officer(s) | Timescale | Metric | NHS People Plan Theme | RAG rating |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Embed EDI interventions into the recruitment process 2. Ensure that the development of the UHL Employer Brand includes the integration of EDI 3. Ensure that our Executive Search and Recruitment Partners are supporting the Trust to fulfil its EDI ambitions | - Ensure that all JDs and person specifications are accessible and free from ableness bias - Roll-out an equality information disclosure campaign to encourage higher disability declaration rates - Ensure inclusive and accessible messaging e.g. employer brand collateral in accessible formats - Disability workforce representation ambitions reflected in contractual relationship with Executive Search and Recruitment Agencies - Monitor disability status of candidates on longlists and shortlists | Head of Recruitment / Head of EDI / Head of People Services Head of Recruitment / Head of EDI / Head of People Services Head of Recruitment /Head of EDI / Head of People Services Head of Recruitment/ Head of EDI / Head of People Services Head of Recruitment/ Head of EDI / Head of People Services | TBC TBC TBC TBC TBC | Metric 1: Percentage of staff in AFC pay bands or medical and dental subgroups and Very Senior Managers including Executive Board members compared with the percentage of staff in overall workforce UHL outcomes 2018/19 Disabled staff 4% of overall workforce Lower representation in all bands except 1-4 2019/20 Disabled Staff 4% of overall workforce. Bands under 1 and 1-4 4.6%, Bands 8C-9 and VSM 4.17% 2020/21 Disabled Staff 4.58% of overall workforce, higher for non-clinical 5.8%. Lower % at more senior levels in the organisation. | Growing for the Future Belonging in the NHS | 4 |
| 4. Ensure our recruitment panels have diverse representation 5. All panellists to undergo bias development 6. Explore proportionate use of the ‘Equal Merit Principle’ at the appointment stage for disabled people 7. Ensure that all recruitment panels incorporate a UHL EDI statement at the interview stage with commitment to mitigate and minimise ‘Ableness’ bias within decision-making | - Ensure where practicable there is disability representation on recruitment panels - Design and launch a bias development module and online toolkit for leaders and managers inclusive of ‘ableness’ bias content - Build upon disability confident measures at shortlisting, and extend use of section (159) positive action measures at the appointment stage - Mitigate the risk of ableness bias occurring during the interview stage of the recruitment process by asking panel Chair to read out an EDI statement before deliberations | Head of Recruitment/ Head of EDI Head of Recruitment/ Head of EDI Head of Recruitment/ Head of EDI Head of Recruitment/ Head of EDI | TBC TBC TBC TBC | Metric 2: Relative likelihood of Disabled staff compared to non-disabled staff being appointed from shortlisting across all posts UHL outcomes 2018/19 Non-disabled 1.37 more likely to be appointed than disabled 2019/20 Non-disabled 1.32 times more likely to be appointed from shortlisting than disabled 2020/21 Non-disabled 1.37 times more likely to be appointed from shortlisting | Growing for the Future Belonging in the NHS | 4 |
| 8. Develop and Implement the Inclusive Decision-Making Framework and pilot programme | - Use the six steps of the IDMF to conduct a review of the capability procedure and the impact on disabled staff | Head of EDI / Heads of People Services | TBC | Metric 3: Relative likelihood of Disabled staff compared to non-disabled staff entering the formal capability process, as measured by entry into the formal capability procedure. UHL outcomes 2018/19 2.36 times more likely to enter the capability process if disabled 2019/20 5.79 times more likely to enter the formal capability if disabled but overall more cases 2020/21 3.66 times more likely to enter formal capability if disabled | Belonging in the NHS Looking After Our People | 1 |
| 9. Develop and embed an Active Bystander (AB) Programme to address inappropriate and unacceptable behaviours and support an inclusive culture | - Undertake a phased roll out of the AB development programme across UHL - Ensure communications messages for the Active Bystander Programme and the YourVoice project incorporate awareness of ableism, and ableness bias. Target communications at key touch points e.g. Disability History Month / Anti-bullying week / Mental Health week | Active Bystander Programme Group Active Bystander Programme Group / YourVoice project group / Culture Shift | TBC TBC | Metric 4: a) Percentage of Disabled staff compared to non-disabled staff experiencing harassment, bullying or abuse from i.) Patients/Service users, their relatives or other members of the public ii) Managers iii) Other colleagues UHL Outcomes 2018 Patients -Disabled Staff 34.3% - Benchmark 34.4% Non-Disabled 24.1% Benchmark 26.9% Other Colleagues-Disabled Staff 30.9% Benchmark 28.3% Non-Disabled 20.1% Benchmark 18.9% Managers- Disabled Staff 21.2% Benchmark 20.% Non-disabled 12.1% Benchmark 12.1% 2019 Patients - Disabled Staff 32.2%, Benchmark 33.9% Non-Disabled 25 % Benchmark 27.3% Other Colleagues-Disabled staff 28.1% Benchmark 27.7% Non-Disabled 17.7% Benchmark 18.4% Managers -Disabled Staff 20.5% Benchmark 19.7% Non Disabled10.3% Benchmark 11.0% 2020 Patients - Disabled Staff 30%, Benchmark 30.9% Non-Disabled 22 % Benchmark 24.5% Other Colleagues Disabled staff 28.4% Benchmark 26.9% Non-Disabled 18.5% Benchmark 17.8% Managers - Disabled Staff 18.4% Benchmark 19.3% Non-Disabled 10.4% Benchmark 10.8% | Looking After Our People Belonging in the NHS | 4 |
| 10.Develop and Implement the Inclusive Decision-Making Framework (bullying, harassment and abuse) | - Enhance our Trust approach to reporting of bullying, harassment and abuse at work by ensuring that processes are transparent, and set out the key routes to reporting incidents including options for anonymous reporting - Implement and embed the YourVoice Report & Support tool - Ensure that ableism and ableness bias is defined within in our B&H processes, policies and procedures | Civility & Respect Stakeholder Group/ Heads of People Services YourVoice project group and Culture Shift Head of EDI and Heads of People Services | TBC TBC TBC | Metric 4: b) Percentage of Disabled staff compared to non-disabled staff saying that the last time they experienced harassment bullying and abuse at work, they or a colleague reported it UHL Outcomes 2018 Disabled staff 49.1% Benchmark 44.2% Non-Disabled Staff 42.% Benchmark 44.4% 2019 Disabled staff 42.7% Benchmark 46.7% Non-Disabled Staff 43.9% Benchmark 45.6% 2020 Disabled staff 42.8% Benchmark 47% Non-Disabled Staff 44% Benchmark 46.1% | Belong in the NHS Looking After Our People | 1 |
| 11. Identify and develop career development pathways for diverse cohorts of staff using talent management methodology 12. Implementation of the High Potential Scheme and alignment to implementation of the Model Employer ‘Aspirational Targets expand to include Gender, Disability, and LGBT+ staff in addition to BAME staff | - Undertake a review of career pathways for the following areas and include a focus on advancing disability equality: - Nursing roles - Head of Service roles - Estates and Facilities roles - Implement and embed the High Potential Scheme and ensure that the national requirement to encourage participation from potential leaders with disabilities | OD Specialist Lead EDI HWB / Deputy Chief Nurse Workforce OD Specialist lead for the High Potential Scheme / Head of EDI | TBC TBC | Metric 5: Percentage of Disabled Staff compared to non-disabled staff believing that the trust provides equal opportunities for career progression or promotion UHL Outcomes 2019 Disabled staff 75.3% Benchmark 79.1% Non-Disabled staff 82.8% Benchmark 85.6% 2020 Disabled - 79.9% Benchmark 79.6% Non-Disabled - 82.7% Benchmark 86.3% | Growing for the Future Belonging in the NHS New Ways of Working and Delivering Care | 1 |
| 13. Ensure that every member of staff includes an EDI objective in their annual appraisal | - Ensure the effective implementation of reasonable adjustments and the talent management of disabled staff forms part of the performance management process of all supervisors and managers | OD Specialist Lead EDI HWB / Head of EDI / People Partners | TBC | Metric 6: Percentage of Disabled Staff compared to non-disabled staff saying that they have felt pressure from their manager to come to work, despite not feeling well enough to perform their duties UHL Outcomes 2018 Disabled Staff 33.5 % Benchmark 37.3% Non-Disabled 25.8% Benchmark 23.9% UHL Outcomes 2019 Disabled Staff 39.4% Benchmark 32.7% Non-Disabled 23.9% Benchmark 22.4% UHL Outcomes 2020 Disabled Staff 35.4% Benchmark 33% Non-Disabled 23% Benchmark 23.4% | Belonging in the NHS Looking After Our People | 1 |
| 14. Identify and develop career development pathways for diverse cohorts of staff using talent management methodology | - Ensure that staff with disabilities are included in the design of talent management interventions - Highlight internal and external recognition of disabled role models | OD Specialist EDI / HWB UHL Comms Team / Head of EDI | TBC TBC | Metric 7: Percentage of Disabled staff compared to non-disabled staff saying that they are satisfied with the extent to which their organisation values their work. UHL Outcomes 2018 Disabled Staff 35.4% Benchmark 36.3% Non-Disabled 47.2% Benchmark 47.6% 2019 Disabled Staff 49.5% Benchmark 49.5% Non-Disabled 37.6% Benchmark 37.4% 2020 Disabled Staff 35.4% Benchmark 37.4% Non-Disabled 49.2% Benchmark 49.3% | Looking After Our People Belonging in the NHS | 4 |
| 15. Embed EDI into existing and future leadership and management programmes | - Ensure that all line managers are aware of the requirement to effectively implement and review reasonable adjustments - Develop disability equality toolkit and workshop | Head of People Services OD / Head of EDI Head of People Services OD / Head of EDI | TBC TBC | Metric 8: Percentage of Disabled staff saying that their employer has made adequate adjustments to enable them to carry out their work UHL Outcome 2018 Disabled Staff 70% Benchmark 72.1% 2019 Disabled Staff 78.1 % Benchmark 73.3% 2020 Disabled 74.4 % Benchmark 75.5% | Looking After Our People Belonging in the NHS | 4 |
| 16. Raise the profile of our DAV Staff Network with internal and external stakeholders | - Continue to support the DAV Network and its activities to advance disability equality within our Trust - Continue to run regular engagement events for disabled staff to understand their lived experience - Facilitate communication between Staff Networks and our wider workforce e.g. develop Staff Network web presence and social media profile - Facilitate DAV Network members influence on decision-making through the implementation of the IMDF and others channels | DAV Network Chairs / Head of EDI / OD Specialist EDI HWB DAV Network Chairs / Head of EDI / OD Specialist EDI HWB DAV Network Chairs / Head of EDI / OD Specialist EDI HWB DAV Network Chairs / Head of EDI / OD Specialist EDI HWB | TBC TBC TBC TBC | Metric 9: a) The staff engagement score for Disabled staff compared to non-disabled staff and the overall engagement score for the organisation UHL Outcomes 2018 Disabled Staff 6.5 Benchmark 6.6 Non-Disabled 7.0 Benchmark 7.1 2019 Disabled Staff 6.6 Benchmark 6.6 Non-Disabled 7.1 Benchmark 7.1 2020 Disabled Staff 6.5 Benchmark 6.7 Non-Disabled 7.1 Benchmark 7.1 b) Has your Trust taken action to facilitate the voices of Disabled staff in your organisation to be heard Yes – Ongoing work to support and develop our Differently Able Staff network and engagement events for disabled staff from across the Trust | Looking After Our People Belonging in the NHS New Ways of Working and Delivering Care | 4 |
| 17. Ensure that our Executive Search and Recruitment Partners are supporting the Trust to fulfil its EDI ambitions 18. Identify and develop career development pathways for diverse cohorts of staff using talent management methodology 19. Implementation of the High Potential Scheme and alignment to implementation of the Model Employer ‘Aspirational Targets expand to include Gender, Disability, and LGBT+ staff in addition to BAME staff | - Improve the representation of disabled people in our leadership community through embedding positive action(159) measures into the selection processes for Band 8a-VSM roles | Head of EDI / Head of People Services OD / Head of Recruitment | TBC | Metric 10: Percentage difference between the Organisation’s Board voting membership and its organisation’s overall workforce disaggregated: By Voting membership of the Board By Executive membership of the Board UHL Outcomes 2018/19 Overall Trust Board representation of Disabled Staff is 6% 2019/20 Overall Trust Board representation of Disabled Staff is 6%, 8% voting. 2% better than overall staff representation of 4% (voting 4% better) 2020/21 Overall Trust Board representation of Disabled staff is 5%, 14.29% non-voting | Growing for the Future Belonging in the NHS | 3 |